## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1 | Open Account | As an administrator, I want to get the customer's nickname, password, email, gender, and date of birth when they register their account, so that I can open an account for a new customer and enter the account information into the system. | Must Have | 1 | 1.Vertify that a user-friendly registration form is needed to collect the necessary information from customers during registration. 2.Personnel Management System should be able to make sure the information is valid. |  | Planned on 24th March 2025 | Planned on 6th April 2025
2 | Security Verification | As a security-conscious user, I want multi-factor authentication and end-to-end data encryption when I login, so that my financial data is protected against unauthorized access. | Must Have | 1 | 1.In account settings, enable multi-factor authentication to encrypt the data. 2.Vertify users can login their encrypt accounts through the multi-factor authentication. 3.Vertify when users want to interview sensitive data they must pass multi-factor authentication. |  | Planned on 24th March 2025 | Planned on 6th April 2025
3 | Querying User ID | As an administrator, I want to look up users by name or ID, so that I can manage information for this specific user. | Must Have | 1 | 1.The admin dashboard should be able to list all the information, search for a specific customer by nickname or email and manage the information. |  | Planned on 24th March 2025 | Planned on 6th April 2025
4 | Classify Transactions | As an end user, I want the personal finance tracker to classify transactions into categories, So that I can clearly distinguish between different types of spending, such as groceries, rent, entertainment and so on. | Must Have | 2 | 1.Implement a robust transaction categorization system to help you clearly distinguish between different types of spending. |  | Planned on 7th April 2025 | Planned on 20th April 2025
5 | View Categories | As a user, I want to be able to view transaction categorizations and clearly understand which category each expense belongs to, so that I can verify and correct any misclassifications. | Must Have | 2 | 1.Vertify that the personal finance tracker needs to provide a clear and user-friendly interface for managing and reviewing categorized transactions |  | Planned on 7th April 2025 | Planned on 20th April 2025
6 | Expense Editing | As a frequent user, I want to easily edit or delete any transaction record, so that I can correct mistakes or remove outdated entries and keep my financial data accurate. | Must Have | 2 | 1.Provide a simple and intuitive interface that allows users to easily locate the transaction records they need to edit. 2.Allow users to directly modify transaction details such as the amount, date, category, or notes within the application. |  | Planned on 7th April 2025 | Planned on 20th April 2025
7 | Visualization Report | As a end user, I want to see my monthly income and expenses displayed in interactive pie charts and bar graphs, so that I can instantly understand my spending patterns and identify areas for improvement. | Must Have | 2 | 1.Verify that pie charts correctly display the percentage distribution of expense categories. 2.Verify that bar graphs accurately compare monthly income and expenses. |  | Planned on 7th April 2025 | Planned on 20th April 2025
8 | Display of Member Benefits | As a non-member, I want to know all the rights and interests that members have, so that I can decide whether joining the membership or not. | Must Have | 3 | 1.Verify that a dedicated page clearly lists all membership benefits. |  | Planned on 23th April 2025 | Planned on 13th May 2025
9 | Consumption habit Forecasting | As a budgeting user, I want ML algorithms to predict next month's expenses based on seasonal consumption (e.g. Singles' Day), so that the error rate of the proposed budget adjustment is < 10%. | Must Have | 3 | 1.Verify that the ML model identifies and prioritizes seasonal events in historical data. Ensure VIP users’ expense predictions error ≤15%. 2.Verify that if insufficient seasonal data exists for prediction, the system displays a warning and provides a conservative default estimate. | VIP Model | Planned on 23th April 2025 | Planned on 13th May 2025
10 | Manage Cards | As a user, I want to manage multiple bank cards to add or remove them, so that I can efficiently track and control my linked payment methods. | Should Have | 1 | 1.Verify users can successfully add a new bank card by entering valid card details. 2.Ensure users can permanently delete a saved card with a confirmation prompt. |  | Planned on 24th March 2025 | Planned on 6th April 2025
11 | Query User Level | As an administrator, I want to look up users based on a specific level, so that I can issue different benefits to different levels of customers. | Should Have | 1 | 1.Verify that entering a valid user level returns all users assigned to that level. |  | Planned on 24th March 2025 | Planned on 6th April 2025
12 | View the remaining membership time | As a member, I want to easily see my remaining membership time, so that I can know when I need to top up next time and when my membership benefits expire. | Should Have | 1 | 1.Verify that the deadline of membership time is displayed on the user profile page. 2.Verify that if the membership has expired, the interface shows "Membership Expired". |  | Planned on 24th March 2025 | Planned on 6th April 2025
13 | Cash Flow Visualization | As a end user, I want real-time pie/bar charts showing ratio of income to expenditure, so that I can instantly grasp monthly financial health. | Should Have | 2 | 1.Ensure that real-time pie/bar charts showing the ratio of income to expenditure are displayed. 2.Users should be able to quickly understand their financial status through the charts. |  | Planned on 7th April 2025 | Planned on 20th April 2025
14 | Comparison of Budget with Actual Expenditure | As a budget-conscious user, I want to compare my actual spending against my monthly budget in some clear ways, so that I can track my financial discipline and adjust my habits if needed. | Should Have | 3 | 1.Ensure that the system can clearly compare actual spending against the monthly budget. 2.The comparison results should be intuitive and easy to understand. |  | Planned on 23th April 2025 | Planned on 13th May 2025
15 | Consumption Reduction Suggestion System | As an end user, I want the personal finance tracker to give cost - cutting recommendations according to my spending behavior, So that I can reduce unnecessary expenses. | Should Have | 4 | 1.The system should provide cost-cutting recommendations based on the user's spending behavior. 2.Users should be able to easily access and understand these suggestions. | VIP API | Planned on 14th May 2025 | Planned on 26th May 2025
16 | Special Management of Rred Envelope | As a WeChat user, I want automatic detection of red packets sent and received recorded and labeled as "Human relations" category, so that the gift money will not be miscounted as daily consumption. | Could Have | 3 | 1.Verify that all red packets are automatically detected and added to the transaction history. 2.Ensure detected red packets are exclusively labeled under "Human relations". |  | Planned on 23th April 2025 | Planned on 13th May 2025
17 | View membership rewards points | As a member, I want to easily see my membership rewards points, so that I can know how many points I have available. | Could Have | 4 | 1.Make sure that users can clearly see their Membership Rewards points on the membership screen and that they can see what they can do with them |  | Planned on 14th May 2025 | Planned on 26th May 2025
18 | Membership expiration reminder | As a member, I want to receive a timely reminder before the expiration of my membership, so that I can keep my membership. | Could Have | 4 | 1.The system should send timely reminders before the expiration of the user's membership. 2.Reminders should be sent through the user's preferred notification method. 3.Users should be able to take renewal action based on the reminder. |  | Planned on 14th May 2025 | Planned on 26th May 2025
19 | Holiday Reminder | As an end user, I want the personal finance tracker to identify local festivals and events based on my location, So that I can receive reminders that my potential consumption will change during those festive periods. | Could Have | 4 | 1.The system should identify local festivals and events based on the user's location. 2.Users should receive reminders that their potential consumption will change during festive periods. 3.Reminders should include holiday budget suggestions and spending alerts. | VIP | Planned on 14th May 2025 | Planned on 26th May 2025
20 | Financial Health Scoring | As a user focused on financial well-being, I want to receive a monthly financial health score from 0 to 100, based on factors like savings rate, debt ratio, and spending habits, so that I can track my progress and get actionable tips to improve my financial situation. | Could Have | 4 | 1.Verify that the system calculates a financial health score from 0 to 100 based on savings rate, debt ratio, and spending habits. 2.Verify that users receive actionable recommendations to improve their financial health based on their score. | VIP | Planned on 14th May 2025 | Planned on 26th May 2025
21 | Smart over Budget Alerts | As an impulsive buyer, I want the system to flag. Unconventional large purchases (such as spending more than 20% of monthly income in a single day) with push notifications, so that I can reconsider unnecessary purchases. | Could Have | 5 | 1.Verify that the system detects when a user's spending exceeds the allocated budget and triggers an alert. 2.Verify that the alert includes the exceeded amount, spending category, and suggested corrective actions. | On the front page | Planned on 19th May 2025 | Planned on 26th May 2025
22 | AI Predicts Holiday Spending | As an end user, I want the personal finance tracker to analyze past spending data during similar occasions in the same location, So that it can provide me with accurate estimates of how much I might spend during these festive periods. | Want Have | 5 | 1.Verify that the system analyzes past holiday spending patterns and generates an estimated budget for upcoming holidays. 2.Verify that users receive spending predictions with an accuracy rate of at least 90% based on historical data. | VIP | Planned on 19th May 2025 | Planned on 26th May 2025
23 | Holiday Budget Proposal | As an end user, I want the personal finance tracker to help me adjust my budget accordingly, So that I can manage my finances better during local celebrations. | Want Have | 5 | 1.Verify that the system suggests a holiday budget based on past spending, income, and user-defined preferences. 2.Verify that users can adjust the proposed budget before finalizing it for holiday expenses. | VIP | Planned on 19th May 2025 | Planned on 26th May 2025
24 | Exception Monitoring Board | As a risk controller, I want real-time alerts when single-user daily transaction frequency > 20 times, so that suspicious money laundering can be checked in time. | Want Have | 5 | 1.Verify that the system displays real-time alerts for unusual transactions, such as sudden large expenditures or frequent transactions. 2.Verify that flagged exceptions are categorized and prioritized for user review and risk assessment. |  | Planned on 19th May 2025 | Planned on 26th May 2025